SotaTek — Software Development & Consulting   |   Vietnam

# Alba — Golf Social Platform

Production-Readiness Hardening & Go-Live Remediation — Technical Proposal & Estimate

19th June 2026  ·  Version 1.1

Prepared for: Alba (Client)   ·   Prepared by: SotaTek

# OVERVIEW

Alba is a mobile-first golf social platform (iOS + Android) that lets golfers post and discover games/rounds, match with players who fit their preferences, coordinate via real-time chat and notifications, and split the cost of play through in-app payments. The product is already built — a NestJS/Prisma/PostgreSQL backend and an Expo/React Native mobile app, both authenticating the same user through Firebase. This engagement takes that existing codebase from its current ~70–75% state to a secure, reliable, production-grade go-live.

### Core Business Model

•  Social Sports Platform: two-sided social marketplace for golf games and rounds, mobile-first.

•  Game Matching & Coordination: post a game with requirements → players request to join → organizer approves → cost split and collected in-app.

•  Marketplace Payments (Stripe Connect): Stripe Connect collects player payments, holds funds ~2 days for disputes, then pays out organizers.

•  Engagement & Community: chat, live notifications, leaderboards, posts, groups and relationships drive retention.

•  Operational Backbone: course catalogue, complaints/reports moderation, and admin-gated operational controls.

# ASSUMPTIONS

The work scope, architecture and estimate below assume the current technology stack is retained (no rewrite). The remediation hardens and completes the existing system rather than replacing it. Final figures are subject to the open questions listed under Practical Limitations.

### Complete Technical Stack

•  Mobile: Expo / React Native (TypeScript), expo-router file-based navigation, Zustand + React Context state.

•  Backend: NestJS 10 (modular, controller → service → Prisma), REST + Socket.IO gateways.

•  Database: PostgreSQL via Prisma (single schema, snake_case, soft-delete via deleted_at).

•  Auth & Security Layer: Firebase ID-token verification (firebase-admin) + admin guard; ValidationPipe; planned rate-limiting + Helmet.

•  Payments: Stripe Connect (destination charges, organizer payouts, webhooks with signature verification + idempotency).

•  Infrastructure: Railway (target); CI/CD gate (build + lint + test); Redis pub/sub for multi-instance Socket.IO + cache (growth-ready 10k+).

•  Monitoring & Comms: Sentry (already initialized); SendGrid for transactional email (assumption — to confirm).

Security & Compliance:

•  Encryption: at-rest + TLS in transit; secrets resolved from environment, validated at boot.

•  Authentication: Firebase ID token on every authenticated request; admin routes fail-closed.

•  Compliance: UK/EU GDPR in scope — data export/erasure with a 6-year financial-ledger retention carve-out (HMRC). AML handled by Stripe.

•  Money Integrity: money stored as integer pence (no float-for-money), parameterized SQL, Stripe webhook idempotency verified clean.

### System Architecture

Two independent deployables share one Firebase-authenticated user identity. The mobile app talks to the backend over REST (EXPO_PUBLIC_API_URL) and Socket.IO; the backend verifies the Firebase ID token, owns all business logic and persistence, and integrates Stripe for the payment lifecycle. Hardening adds a CI/CD gate, graceful shutdown, environment validation, database indexing/soft-delete enforcement, and Redis-backed horizontal scale.

•  Mobile Client: Expo/React Native app — golfer-facing UI, the only client.

•  Backend API: NestJS REST + WebSocket API — auth, games, payments, chat, notifications, moderation.

•  External Integrations: Stripe Connect, Firebase, Mapbox, push notifications, transactional email.

# ROADMAP & PHASES

### In Scope Functions

A. Security & Access Control

•  Hardening: close IDOR on messages/conversations/complaints; guard /users CRUD, notifications/send-all and leaderboard writes; authenticate WebSocket room joins; fix reflected XSS on /go.

B. Payments & Payouts

•  Completion: one canonical payment flow; server-side Stripe verification (no client-trusted amounts); 2-day hold + automated payout; refund-on-cancel; atomic, idempotent, double-payout-safe writes.

C. Data Layer

•  Hardening: enforce soft-delete globally; add FK / hot-path indexes (concurrent migrations); fix unique constraints ignoring deleted_at; pagination on list endpoints; transactional financial writes.

D. Mobile App

•  Hardening: fix API contract drift (EVENING time-slot, CONFIRMED status); 401 handling + token refresh; ErrorBoundary; remove fake Stripe key fallback; EAS env wiring.

E. Reliability & Infrastructure

•  Platform: CI/CD gate (build + lint + test); graceful shutdown + Prisma disconnect; env validation at boot; hardened Dockerfile; Helmet/throttler/CORS; Redis adapter for multi-instance scale.

F. Compliance, Legal & Comms

•  UK/EU: GDPR data export/erasure with financial-ledger retention; store-mandatory privacy/consent flows; transactional email (SendGrid).

G. Performance & Scale

•  Growth-ready 10k+: remove N+1 in payout review; cache suggested/nearby; search indexing (pg_trgm); rate-limit defaults; WebSocket scale; moderation enforcement; mobile react-query.

H. Quality & Testing

•  Quality Gate: coverage gate for money/auth/games critical flows; mobile smoke + critical-flow tests (built from near-zero).

### Roadmap

Agile delivery in 2-week sprints over ~8 weeks (2 months) with a dedicated parallel squad — compressed from a sequential 4-month plan by running three backend tracks plus mobile concurrently. Phase 1 (P0 blockers) gates everything; once blockers clear, the remaining workstreams run in parallel across four tracks (T1 Security & Payments, T2 Data/Performance/Compliance, T3 Infra & DevOps, T4 Mobile), with testing threaded throughout.

Sprint 1 (Weeks 1–2) — P0 Blockers + CI Foundation

•  Focus: eliminate every go-live-blocking exploit and stand up the quality gate before parallel work begins.

Key Deliverables:

•  T1 Backend: close all IDOR/access-control holes, authenticate sockets, guard admin/user/leaderboard routes, fix client-trusted payment verification, make double-payout atomic/idempotent.

•  T3 Backend: graceful shutdown + Prisma disconnect; env validation.

•  T3 DevOps: stand up CI/CD gate (build + lint + test).

•  T4 Mobile: begin API-contract reconciliation in parallel.

Sprint 2 (Weeks 3–4) — Payments, Data & Infra (parallel)

•  Focus: one canonical, atomic, automated payment lifecycle on a hardened, scalable platform.

Key Deliverables:

•  T1 Backend: canonical flow, 2-day hold + auto-payout, refund-on-cancel.

•  T2 Backend: soft-delete enforcement, FK/hot-path indexes, pagination.

•  T3 Infra: hardened Dockerfile, Helmet/throttler/CORS, Redis adapter for Socket.IO + cache (multi-instance).

•  T4 Mobile: 401/refresh, ErrorBoundary, remove fake key, EAS env.

Sprint 3 (Weeks 5–6) — Compliance, Scale & Completeness (parallel)

•  Focus: UK/EU + store readiness, growth-ready performance, production-clean code; test build-out ramps up.

Key Deliverables:

•  T2 Backend: GDPR export/erasure with ledger retention; consent/privacy flows; SendGrid transactional email.

•  T2 Backend: remove N+1, caching, pg_trgm search index, rate-limit, WebSocket scale, moderation enforcement.

•  T1/T2 Backend: live-stub completion, timezone correctness, CVE patching, /v1/games sunset.

•  T4 Mobile: react-query data layer + game-performance optimizations.

•  QC: coverage build-out for money/auth/games + mobile smoke tests.

Sprint 4 (Weeks 7–8) — Quality Gate, UAT & Go-Live

•  Focus: verified, tested, deployed.

Key Deliverables:

•  QC: coverage gate enforced for money/auth/games; mobile critical-flow tests green in CI.

•  All: staging deploy, UAT, bug-fix, production deploy + handover docs.

### Practical Limitations

•  Payment-flow decision: final figures depend on confirming the canonical payment flow (/games vs /v1/games) and whether the client-trusted endpoint is still live.

•  Endpoint intent: whether public endpoints (leaderboards, round, locations, courses/profiles CRUD) are intended features or leftover scaffold.

•  Deploy targets: Railway deploy target and instance count (drives the Redis adapter decision); EAS production env vars must be set on the dashboard.

•  Assumptions to confirm: financial-data retention period and email provider (SendGrid assumed); search backend (pg_trgm assumed); rate-limit thresholds.

•  Mobile test build-out: mobile testing is built from near-zero (~162 files / ~34k LOC, native Stripe/Firebase/Mapbox mocks) — the single largest variable in the range.

### Out-of-Scope Features

•  Large refactors: god-service refactor (games ~2,200 LOC) — high regression risk on money code; deferred post-launch.

•  Exhaustive coverage: broad/strict-mode test coverage beyond money/auth/critical flows — deferred post-launch.

•  a11y & i18n: accessibility (a11y) and internationalisation (i18n) — deferred post-launch backlog (~11–17 md when undertaken).

•  New features: no new product features; engagement is hardening/completion of the existing scope only.

•  Heavy infra: Elasticsearch/full-text search; native AML (handled by Stripe).

# DELIVERABLES

On completion the Client receives a production-ready system plus the supporting artefacts:

•  Hardened backend + mobile source code: all remediation merged to main, passing the CI/CD quality gate.

•  Go-live gate sign-off: 0 open Critical security/money findings; checklist evidence per phase.

•  Automated payment lifecycle: single canonical flow with hold, payout, refund — atomic and idempotent.

•  Database migrations: indexes, soft-delete enforcement, constraint fixes (concurrent, reversible).

•  CI/CD + infrastructure config: pipeline, hardened Dockerfile, env validation, Redis-backed scale.

•  Test suites & coverage report: money/auth/games gate + mobile smoke / critical-flow tests.

•  Compliance package: GDPR export/erasure, consent flows, transactional email.

•  Deployment & handover guide: runbook, environment matrix, UAT report, operational docs.

# SCHEDULE & COST

## Working Breakdown Structure

Delivery is agile (2-week sprints) with a parallel squad. The WBS below groups the remediation scope by workstream; effort is point-estimated per item and rolled into the cost model.

| # | Category | Function | Sub-Function | Notes |
| --- | --- | --- | --- | --- |
| A. Security & Access Control |  |  |  |  |
| A1 | Access control | IDOR remediation | Messages, conversations, complaints (PII) |  |
| A2 | Access control | Route guards | /users CRUD, notifications/send-all, leaderboard writes |  |
| A3 | Real-time | Socket authentication | Authenticate room joins (no eavesdrop/inject) |  |
| A4 | Web | Reflected XSS fix | /go attribution endpoint |  |
| B. Payments & Payouts |  |  |  |  |
| B1 | Payments | Server-side verification | No client-trusted amount/intent |  |
| B2 | Payments | Canonical flow | Resolve /games vs /v1/games |  |
| B3 | Payments | Hold + auto-payout | 2-day hold, scheduled payout, refund-on-cancel |  |
| B4 | Payments | Atomicity & idempotency | Double-payout-safe, transactional writes |  |
| C. Data Layer |  |  |  |  |
| C1 | Database | Soft-delete enforcement | Global; honour deleted_at on reads |  |
| C2 | Database | Indexing | FK + hot-path indexes, concurrent migrations |  |
| C3 | Database | Constraints + pagination | Unique-with-deleted_at; list pagination |  |
| D. Mobile App |  |  |  |  |
| D1 | Mobile | Contract reconciliation | EVENING time-slot, CONFIRMED status drift |  |
| D2 | Mobile | Auth resilience | 401 handling + token refresh |  |
| D3 | Mobile | Stability | ErrorBoundary; remove fake Stripe key; EAS env |  |
| E. Reliability & Infrastructure |  |  |  |  |
| E1 | DevOps | CI/CD gate | Build + lint + test blocks deploy |  |
| E2 | Infra | Runtime hardening | Graceful shutdown, env validation, Dockerfile |  |
| E3 | Infra | Edge hardening | Helmet, throttler, CORS, Swagger gating |  |
| E4 | Infra | Horizontal scale | Redis adapter for Socket.IO + cache |  |
| F. Compliance, Legal & Comms |  |  |  |  |
| F1 | Compliance | GDPR export/erasure | Ledger retention carve-out (6 yr) |  |
| F2 | Compliance | Consent & privacy flows | Store-mandatory readiness |  |
| F3 | Comms | Transactional email | SendGrid integration |  |
| G. Performance & Scale |  |  |  |  |
| G1 | Performance | Query optimization | Remove N+1, caching |  |
| G2 | Scale | Search + rate-limit | pg_trgm index, rate-limit defaults |  |
| G3 | Scale | WS scale + moderation | WebSocket scale, moderation enforcement |  |
| G4 | Mobile | react-query + game perf | Client data layer + perf |  |
| H. Quality & Testing |  |  |  |  |
| H1 | QA | Coverage gate | Money/auth/games critical flows |  |
| H2 | QA | Mobile tests | Smoke + critical-flow (from near-zero) |  |
| I. Out of scope (deferred post-launch) |  |  |  |  |
| I1 | Refactor | God-service refactor | <Not in scope> |  |
| I2 | QA | Broad/strict coverage | <Not in scope> |  |
| I3 | UX | a11y + i18n | <Not in scope> |  |

## Cost & Budget estimation

Investment required to take Alba from its current state to production go-live, delivered by a dedicated SotaTek squad. Pricing is time-and-materials by role in man-months (M/M); USD.

Recommended Scope — Production Go-Live (~8 weeks / 2 months)

Customer-confirmed scope = full hardening (Phases 1–11, growth-ready 10k+, UK/EU compliance, production-grade stubs, Redis) excluding the deferred god-service refactor and broad/strict test coverage. Total engineering effort ≈ 150–186 man-days; the table prices the point estimate within that range. Calendar time is halved versus a sequential plan by running three backend tracks plus mobile in parallel — the total effort and cost are unchanged.

| Position | Month 1 | Month 2 | Total (M/M) | Unit Price (USD) | Total Cost (USD) |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 0.5 | 0.5 | 1 | 3,500 | 3,500 |
| BA & UI/UX Designer | 0.5 | 0.25 | 0.75 | 3,000 | 2,250 |
| Backend Engineer (x3) | 3 | 3 | 6 | 3,000 | 18,000 |
| Mobile Engineer | 0.75 | 0.75 | 1.5 | 3,000 | 4,500 |
| QC Engineer | 0.5 | 1 | 1.5 | 2,800 | 4,200 |
| DevOps Engineer | 0.5 | 0.25 | 0.75 | 3,600 | 2,700 |
| TOTAL | 5.75 | 5.75 | 11.5 |  | 35,150 |

Recommended-scope investment: USD 35,150  (≈ 11.5 man-months across the squad, delivered in ~2 months).

•  Optional add-on: the deferred god-service refactor and broad/strict coverage are available as a post-launch add-on (~14–18 md, ~USD 6,000–7,500) once the product is live.

•  Future phase: a11y + i18n localisation can be scoped separately post-launch (~11–17 md).

•  Aggressive timeline: a ~6-week (1.5-month) variant is feasible if compliance (F) and growth-scale (G) are deferred to a fast-follow and the launch targets the go-live blockers only (A–E + targeted H).

Estimate is a presale range; final figures confirmed after the open questions above are answered (±~5 md).

# PAYMENT MILESTONE

Payments are tied to verifiable delivery milestones; total equals 100% of the engagement fee.

| Milestone | Deliverable | Percentage | Due Timeline |
| --- | --- | --- | --- |
| M1: Contract Signing | Signed agreement, squad mobilisation, kickoff | 40% | Upon contract execution |
| M2: P0 Blockers Demo | 0 open Critical findings; payments + access-control demo on dev | 30% | End of Sprint 2 (~Week 4) |
| M3: Staging & UAT | Full scope on staging; UAT begins | 20% | End of Sprint 3 (~Week 6) |
| M4: Go-Live | UAT sign-off, production deploy, handover docs | 10% | End of Sprint 4 (~Week 8) |

Total: 100%